## 2026 Full List
2026 Priority Project List Updates
Project Name | Location/ Sponsor | Contact | Update Rec'd | Project Description and Update | Priority Area/s | Timeline | Estimated Costs | Estimated Jobs | Funding Sources
Halls Village Road Reconstruction | Chester | Andrew Hadik (Town Planner) | 2026-03-18 | DESCRIPTION: The project is intended to upgrade approximately 1.2 miles of a narrow and poor condition Class V town road. The project also includes the upgrade of two undersized culvert locations for stream crossings which have occasionally overtopped the road. HVR is a bypass that is heavily used as a connector by the residents of Chester and the surrounding towns of Derry, Sandown, and Fremont, and also commercial trucking and contracting traffic operating regionally in this area. UPDATE: The surveying, geotechnical borings, hydrological & hydrologic engineering for the culverts, and the under-drainage, new ditches, gravel shoulders, driveway culverts, and reconstruction and paving of the wearing course for the road have all been completed. The two culverts still need to be replaced; however, these are being postponed because of the lack of funding. When to pave the wearing course has not yet been decided, but it should occur only after the culverts are replaced. | IU, E | Initial site work and engineering has been completed Construction in phases: July 2028 - November 2030 | #162 HVR Culvert $1,230,000 + #256 HVR Culvert $1,485,000 = $2,715,000 | ~18 temporary jobs; retaining ~12 for businesses on HVR | Grants, Municipal
Abbott Court | Derry | Bev Donovan (Economic Development Director) | 2026-03-12 | DESCRIPTION: This project will provide a public parking garage with retail and workforce/affordable housing components above. A potential second commercial building is being considered. UPDATE: After addressing abutter issues and some other issues pertaining to lot-line adjustment and final petroleum cleanup, Phase One is underway, and includes a 300+ space parking garage and 114 apartments. | H, T | Phase One should conclude within 18 months; Phase Two is still in planning stage. | $40+ million | 25 new/ retained | Municipal Bond; Public/Private; Direct Sale; Grants
Derry Rail Trail Extension | Derry | Bev Donovan (Economic Development Director) | 2026-03-12 | DESCRIPTION: This project will extend the existing Derry Rail Trail to the Londonderry town line, tying into the regional trail system and Granite State Rail Trail system. The proposed extension is 1,900 feet. UPDATE: With the settlement of the Exit 4-A tunnel lawsuit, the NH DOT will be constructing a tunnel under the new roadway, leading to the completion of the rail trail connection between Derry/Londonderry. This ties into the Granite State Rail Trail System. | T, E | In-progress. | 970000 | temporary construction jobs | Federal Transportation Alternative Funds, NH DOT, Municipal
Derry Route 28 Sewer Interception Extension | Derry | Bev Donovan (Economic Development Director) | 2026-03-12 | DESCRIPTION: Extend the sewer line from Route 28 at Berry Rd south to Ryan's Hill as identified in the town's Master Plan. The extension includes 105+/- acres of commercially-zoned properties, much of which remains vacant. As Derry has very limited commercial land available for development, public sewer would maximize the economic development of this area. 3,600' of gravity sewer line and 1,925' of pressure line is proposed. UPDATE: Project back on schedule after a delay from 2025. | IU | work scheduled to begin in 2026. | $4.2 million | UNK | Municipal bond, Water Wheeling revenues
New Police Station and Fire Substation | Exeter | Darren Winham (Economic Development Director) | 2026-04-03 | DESCRIPTION: Construct an approximately 23,000 square foot new police station and fire substation. The existing police department will be relocated to the new facility and a portion of the downtown fire station will be relocated to the new substation. UPDATE: Project underway. Construction began in November 2025. Substantial completion is expected by the end of 2026. | IU, CV | 2024-2026 | 18082500 | N/A | InvestNH Grant, Municipal bond
Squamscott River Sewer Siphons & Webster Avenue Pump Station | Exeter | Darren Winham (Economic Development Director) | 2026-04-03 | DESCRIPTION: This is a two phase project to increase sewer capacity which will allow for future growth and prevent the likeliness of sanitary sewer overflows. The first phase includes replacing three parallel inverted sewer siphon pipes under the Squamscott River. The second phase includes upgrading the current flow capacity at the Webster Avenue sewage pump station. UPDATE: Construction continued through 2025 and into early 2026. The Pump Station and Force Main are now operational. The project reached substantial complete in March 2026. Pump list items will be addressed in the Summer of 2026, with full project completion expected by the end of 2026. | IU | Construction is underway, completion estimated in 2026 | 13106000 | N/A | SRF Loan, CDS (federal), NH ARPA, NH DES CWSRF Grants, Municipal
Hampton Wastewater Treatment Plant | Hampton | Jen Hale (DPW Director) cc James Sullivan (Town Manager) | 2026-03-10 | DESCRIPTION: Implementation of a three-phase design and construction project necessary to ensure continued reliable and efficient operation of the town's existing wastewater treatment plant and to comply with the town's effluent discharge permit. UPDATE: Phase II has been awarded to Northeast Earth Mechanics, LLC and is ongoing. | IU | Phase 1: Completed Phase 2: Estimated completion in late fall 2027 Phase 3: UNK | Phase 2: $15,700,000 | UNK: but will retain jobs and allow for future development | Municipal, CWSRF, ARPA, SAG/SAG Plus
Winnacunnet Road Reconstruction | Hampton | Jen Hale (DPW Director) cc James Sullivan (Town Manager) | 2026-03-10 | DESCRIPTION: Reconstruction of Winnacunnet Road from Lafayette Road to Ocean Boulevard. Includes replacement of failing utility infrastructure and sidewalks, as well as surfacing of the roadways. UPDATE: No changes in the past 12 months. | IU | 2028+ | 12705000 | N/A | TAP, CWSRF, Municipal
Hampton Route 1A Improvements | Hampton/ Hampton Beach Area Commission | Pat Bushway (Hampton Beach Area Commission Chair) cc: Barbara K. (RPC Commissioner) | 2026-03-06 | DESCRIPTION: Design, engineering, and complete reconstruction of the roadway, infrastructure, and sidewalks for critical sections of Ocean Blvd (Route 1A) from the new Seabrook-Hampton Bridge (currently known as the Neil R Underwood Bridge) to the High Street intersection. Work shall be in concert with the design and construction of the new Seabrook-Hampton Bridge. UPDATE: A public hearing for the project was held on August 13th, 2025, at Winnacunnet High School in Hampton. Design of Phase 1 is underway. | IU, T | Phase 1 is in design, with construction planned for 2027. | Phase 1: engineering & partial construction $9.9 million Phase 2: construction $52-70 million | UNK | UNK
Hampton U.S. 1/NH 101 Interchange Realignment | Hampton/ RPC | Scott Bogle (RPC) | 2026-01-13 | DESCRIPTION: Realignment of the U.S. Route 1 and NH Route 101 interchange in Hampton. UPDATE: The project (Hampton 41584) saw a major setback in 2025 in being removed from NHDOT's draft 2027-2036 Ten Year Transportation Plan (TYP) in a as part of a significant overhaul to bring the plan into fiscal constraint. While the project could be restored to the TYP by the Legislature, the likelihood is that it will need to be either 1) brought forward again through the MPO process for inclusion in the TYP, or 2) proposed for funding under a nationally competitive grant program such as Safe Streets and Roads for All (SS4A) or BUILD. The project remains a priority in the RPC MPO Long Range Transportation Plan. | IU, T | Uncertain, but long-term | $8.1 million (2029 dollars) | UNK | National Highway System (NHS); Surface Transportation Block Grant (STBG); State, Local
The Village on Technology Hill PUD | Londonderry | Kellie Caron (Assistant Town Manager & Director of Economic Development) | None Received | DESCRIPTION: The Village on Technology Hill PUD is a mixed-use development encompassing approximately 110 acres. The project is organized into 3 primary zones: Industrial - this area includes approximately 330,000 square feet of industrial and office space Residential - this area includes a residential development of 439 market rate units distributed across 9 buildings offering one-, two-, and three-bedroom units. The buildings encircle a village green featuring amenities such as a playground and dog park. Commercial - this area includes a general retail store and childcare facility serving residents and employees of nearby businesses. UPDATE: No update received. Project on one-year probation period. | H, C, W, CV | Project started in 2024 and is ongoing | Total construction cost estimated at $160 million | 300+ jobs | Private developer
Woodmont Commons Project | Londonderry | Kellie Caron (Assistant Town Manager & Director of Economic Development) | None Received | DESCRIPTION: Development of a 600-acre mixed-use, approved Planned Unit Development (PUD) Master Plan. Permitted for up to 1.8 million square feet of commercial space, over 1,400 residential dwelling units, plus hotel, institutional, and civic uses. UPDATE: No update received. Project on one-year probation period. | H, IU, W | On-going | UNK | Phase 1: 600 new jobs; Remaining Phases: over 3,000 new jobs | Private Developer
Imagine Main Street | Nashua | Liz Hannum (Director of Economic Development) | 2026-03-26 | DESCRIPTION: Designing Main Street to function as a destination instead of a thruway. The city is committed to building on the momentum from the significant recent and ongoing investments in our downtown and realize the community-led vision for Main Street outlined in the recently adopted Master Plan, Imagine Nashua. Continued investment in our downtown, comprised almost entirely of neighborhoods identified by the DOT as Areas of Persistent Poverty and Historically Disadvantaged Communities, will increase economic opportunities and improve quality of life for our residents. The Imagine Main Street project will directly confront the inequities the current vehicle-oriented design of the corridor creates for those without personal vehicles, as well as incorporating green infrastructure to help mitigate the disproportionately negative environmental impacts on residents of the proposed project area. Nashua's downtown is an important economic driver of the city, and the city strives to make it a welcoming, walkable, and enticing destination for residents and visitors alike. UPDATE: No changes. The project is on hold, moved from Intermediate-term list. | T, CV | UNK | $30+ million | 0 | BRICK funding
Nimco Redevelopment | Nashua | Liz Hannum (Director of Economic Development) | 2026-03-26 | DESCRIPTION: The redevelopment of a city-owned parcel of land known as the "Nimco Property," a defunct building with adjacent land area on a brownfield site. The property is approximately 3+ acres in land area. It is located in downtown Nashua off the Veterans Memorial Parkway and the Nashua River. It will need environmental cleanup, demolition of the existing mill building, and redevelopment of housing. UPDATE: The developer purchased the neighboring Bagshaw site and it redesigning the site plan. Demolition of NIMCO and neighboring Bagshaw site completed. Master Development Agreement executed. | H, E | 3 years for 254 units. | Demolition: $1.5 million; Construction: UNK | 25 | Private Developer
Nashua Public Library | Nashua | Liz Hannum (Director of Economic Development) | 2026-03-26 | DESCRIPTION: The Nashua Public Library Building is in need of a full renovation to bring the building up to code. This includes major improvements to the accessibility of the bathrooms, stairs, sprinklers, lighting, etc., as well as a complete overhaul of the building envelope inside and out. This will also include a programmatic study of what the modern library needs. It is currently being used for a library and a de facto community center and will need to make major improvements to the physical space in order to accommodate the modern uses of the library. UPDATE: Completed feasibility of 4 scenarios of redevelopment and concluded that we would move forward with an addition. Received $1m bond for design work. Contracted architect and CM services. | CV | Design work will commence spring 2026 and last one year. | $35-50 million | 45 | Municipal bond
Mohawk Tannery Cleanup & Development | Nashua | Liz Hannum (Director of Economic Development) | 2026-03-26 | DESCRIPTION: The old Mohawk Tannery is being redeveloped into 540 housing units including some affordable units. The site is Brownfield, and the first step in this process is environmental cleanup from the tanning activities that have left toxic chemicals in most of the property. The next step is apartments, with 20% affordable, and then condos. There will be six buildings and a very large public open space and a pedestrian bridge over to Mine Falls Park. UPDATE: Remediation began in November 2025. Project is underway, moved from Intermediate-term list. | H, E | 2 years for remediation, 5 years for 534 housing units. | Cleanup: $27 mil; Site development: $300+ million | 15 | EPA, Housing Revolving Loan Fund, Private investment
Redevelopment of Elm Street School | Nashua | Liz Hannum (Director of Economic Development) | 2026-03-27 | DESCRIPTION: The Elm Street Middle School closed in June 2024 and reverted to city ownership. After community outreach and input, the city is focusing on midrise housing for the site, possibly reusing the building and maintaining the Keefe Auditorium as a public theater. The project has gone out for RFP to see what private development can bring to the project. We hope to see at least 300 housing units over the entire acreage and a reinvestment in the Keefe Auditorium. UPDATE: The project has narrowed the proposals down to two qualified developers, but they are two very different proposals. Because the city has not determined what to do with the Keefe Auditorium yet, there has been a hold until we can price out some options. One proposal provides a large space for the city to develop the Keefe and the other provides very little space, but the purchase price is significantly higher that would be able to cut the cost down to renovate the Keefe. We are waiting on those estimates to determine which developer's proposal will fit best with that vision. | H, CV | Select developer in 2026, start construction in 2028. | $50 million | 20 | Private developer
McIntyre Road Bridge Replacement (formerly McIntyre Road Bridge Study and Intersection Design) | Newington | Paul Deschaine (Newington) | 2026-04-02 | DESCRIPTION: Town owned McIntyre Bridge, was built in 1972 as a public roadway crossing Pease Air Force Base. A 2024 NHDOT bridge inspection rated the bridge deck width “intolerable” listed for high priority replacement. This project will perform a feasibility study of alternatives including the possible bridge and fill removal to provide an at-grade intersection of McIntyre Road/Arboretum Drive and enhanced public access, reducing resident travel distance by 2.5 miles. UPDATE: Based on the 2024 NHDOT inspection, this project has been updated to include the replacement of the bridge. The town has applied for a Federal Lands Access Program (FLAP) Grant. | IU, E | Immediate once funding is secured, with public outreach and preliminary design in year 1 and construction following in year 2. | 2776227 | UNK | Federal Lands Access Program (FLAP) Grant; Municipal funding
Newington Port Roadway Improvements | Newington/ Newington and Portsmouth | Paul Deschaine | 2026-02-15 | DESCRIPTION: The project involves the full depth reconstruction of approximately 2,700 LF or 74,800 sf of roadway along the eastern portion of Gosling Road, and 11,330 LF or 401,100 sf of Shattuck Way in order to improve the base material of each roadway resulting in improve load capacity. In addition, certain portions of Shattuck Way will be raised and the corresponding drainage improved to correct the flooding conditions that have been experienced. The proposed improvements will enhance the roadways’ sustainability and reliability as the primary access route to other inland transportation corridors. UPDATE: The portion of the project that remains is the entire length of Shattuck Way and the easterly portion of Gosling Road from the intersection of Woodbury Avenue. The town submitted an application for a Port Infrastructure Development grant with the US DOT and are waiting a decision. Cost estimates were updated. | IU | 2026-2029. Two years once funding is secured. | 3294783 | UNK | Federal transportation grant (80%), municipal funding (20%)
1035 Lafayette Rd. Workforce Housing Development | Portsmouth/ Portsmouth Housing Authority | Craig Welch (Executive Director PHA) | 2026-04-13 | DESCRIPTION: This project will create 44 units of permanently affordable housing, including a mix of one-, two-, and three-bedroom apartments serving individuals and households earning approximately 60% of Area Median Income (AMI). The site will be served by the COAST Bus system, and the development will include an on-site childcare center. The development will also be home to HAVEN, a statewide domestic and sexual violence support organization, which will establish its headquarters on-site, deliver community-based services, and create 7 units of transitional housing for individuals and families in need of safe, stable housing. Additional nearby community resources include a local church and the Black Heritage Trail of New Hampshire, reinforcing opportunities for connection, cultural engagement, and community support. A targeted leasing preference for childcare workers will further support the local workforce by helping stabilize and retain employees in a sector critical to regional economic health and family well-being. UPDATE: Ground breaking in late spring 2026. New project. | H, C, T, E, CV | Late spring 2026 - Ground Breaking Lease up H1 2028 | Approx. $28.5 million | UNK, Temporary construction jobs, property management & maintenance, childcare center, HAVEN center services | M&T Bank for Low-Income Housing Tax Credit Equity investment, Construction and Perm financing by Newburyport Bank, New Hampshire Housing, InvestNH Funding, NH CDFA Tax Credits, Federal Home Loan Bank of Boston Affordable Housing Program, Eversource Energy, PHA Ltd. Deferred Developer Fee and Sponsor Loan, City of Portsmouth, Granite State Development Grant, Private Foundation grants.
Sherburne School Workforce Housing Development | Portsmouth/ Portsmouth Housing Authority | Craig Welch (Executive Director PHA) | 2026-04-13 | DESCRIPTION: The public-private partnership project, located on city-owned land, will deliver a phased, community-centered workforce housing development. Phase 1 will create 90 units of high-quality, energy-efficient workforce housing, with a mix of one-, two-, and three-bedroom apartments, serving individuals and households earning approximately 60% of Area Median Income (AMI). Phase 2 is anticipated to include an additional approximately 30 units of permanently affordable housing, with a focus on artist live-work housing and art-centered community space. The project integrates the housing development with targeted infrastructure and transportation improvements, including necessary upgrades to sewer infrastructure to increase capacity. UPDATE: New Project. | H, IU, T, CV | 2025–2026: Predevelopment, design, permitting, and financing; 2026– 2028: Phase 1 construction; Phase 2: UNK | Phase 1: $36.5 million (includes infrastructure upgrades); Phase 2: unknown. | UNK, Temporary construction jobs. | Low-Income Housing Tax Credit Equity, Conventional Bank Financing, New Hampshire Housing, InvestNH Funding, NH CDFA Tax Credit Equity, Federal Home Loan Bank of NY Affordable Housing Program, Eversource Energy, PHA Ltd. Deferred Developer and Sponsor Loan, City of Portsmouth, others.
U.S. Route 1 Sidepath Construction | Portsmouth | Jill Harris (Principal Planner, Planning and Sustainability Department) cc: Sean Clancy (Assistant City Manager, Economic & Community Development) | 2026-01-20 | DESCRIPTION: Creation of a walkable and bike-able connection for neighborhoods and destinations along Route 1 through construction of ten ft. sidepaths on each side of road in available NH DOT right-of-way. This will be a phased project: the first phase is the design work from the intersection of Elwyn Road/Peverly Hill Road to Heritage Ave. to correspond with the NH DOT Route 1 Corridor. Additional sections will be designed as part of Phase 2, and construction of the project is Phase 3. Because of the corridor project and DOT involvement, final costs may be more that the city portion. UPDATE: No changes since 2025 update. | CV | Planning and Design: 2025-2027; Construction: 2028-2030 | $19.2 to $24.9 million | UNK/Indirect | Capital Improvement Plan, Municipal, State
Salem Bike-Pedestrian Corridor | Salem | Crayton Brubaker (Community Development Program Manager) | 2026-03-12 | DESCRIPTION: The completion of a 5.1 mile rail trail on the former Manchester & Lawrence rail line. The Salem section is the most southern segment of the Granite State Rail Trail, which will run from Salem to Lebanon, NH. Currently the northern (approx.) two miles is paved and complete. Plans and funding are in place for the section from Main St. to Cluff Crossing Rd. Approx. two miles of trail south of Cluff Road remain. There are additional projects that will need to be developed to help support corridor. UPDATE: Phases IV and V (Main Street to Rockingham Park Blvd) are in design and construction is estimated to begin in late 2027. Phase VI (Rockingham Park Blvd to Cluff Crossing Road) construction was completed in 2025. Grant opportunities will be pursued for the remaining phases as they arise. | T, E, CV | Phases I-III, VI are complete; Phases IV-V construction in 2026; Phase VII+ are UNK SHORT TERM | Completed Phases: $3.2 million; Phases IV-V - $1.2 million; Phases VII + unknown | UNK | CMAQ, TTAP, EDA, Impact Fees, Private Developer
Salem Depot Park (Phase 1) | Salem | Crayton Brubaker | 2026-03-26 | DESCRIPTION: In 2025, the Town completed a Depot Master Plan and the Town Council approved a phasing / funding plan for the park improvements. This project covers the design and construction of the first phase of the Salem Depot Park project which includes the construction of a playground, public restroom, storage building, and installation of landscaping, lighting, signage, and updated parking lot configuration across from the newly erected Depot Veterans Memorial Plaza. UPDATE: New Project. | CV | Late 2026 - submit grant application; 2027 - funding, design, permitting; 2028 - construction | 1059576 | N/A | Land and Water Conservation Fund (LWCF) Grant; Recreation Impact Fees; Community Donations; Municipal taxation
Salem Police Station | Salem | Crayton Brubaker (Community Development Program Manager) | 2026-03-12 | DESCRIPTION: The proposed project includes design, demolition of the existing building, construction of the new facilities, and temporary relocation of the Police Department operations during construction. The new Police Station building will be situated on the same site as the existing facility. The new police station will encompass an operational area on two levels of approximately 31,600 square feet (SF), 4,000 SF Training Range, and a 4,000 SF K9 Outbuilding. UPDATE: The Police Station is well under construction and is anticipated to be completed in fall 2026 with move in shortly after. Construction is going smoothly and is on pace with scheduling and budget. | IU, CV | 2024-2026 | $38.6 million | retain 250 jobs | Impact fees, municipal bonds
Southern NH Regional Drinking Water Line | Salem (Salem portion) | Crayton Brubaker | 2026-03-27 | DESCRIPTION: The Southern NH Regional Drinking Water Line Project is a collaborative effort by public and private water entities that involves development, construction, and operation of infrastructure that will interconnect the water systems of Manchester, Derry, Salem, Windham, Atkinson, and Plaistow. The objective of the project is to address current and future drinking water concerns related to methyl tertiary butyl ether (MtBE) contamination. The primary goal is to ensure that a flow of safe and reliable water source providing potable water to and through the aforementioned communities to meet the needs of the water systems and create reliability and sustainability for the present and future. UPDATE: The project began in 2018 with a conceptual design. Between 2020-2026, Phase 1 and a portion of Phase 2 was funded and constructed. The Town has entered into an MOU with the respective parties to work collaboratively to see the project through including the Southern Interconnection Agreement for purchase and sale of water. The Town is actively engaged in engineering services and project construction with Weston and Sampson all paid by New Hampshire Department of Environmental Services. Now the project is waiting for funding. New Project. New Project. | IU | 2026 onwards - Waiting for additional funding for continued construction per the signed Southern Interconnection Agreement in various communities | $30+ million | Hundreds | NH Drinking Water and Groundwater Trust Fund; Municipal Water Funds
Tuscan Village | Salem/ Tuscan Village Development | Crayton Brubaker (Community Development Program Manager) | 2026-03-12 | DESCRIPTION: Redevelopment of the former Rockingham Park Racetrack. The mixed-use project will include multifamily housing, retail, medical offices, office space, a hotel, restaurants, and a car dealership. The total project is 170 acres and will contain close to 2.5 million sq. ft. of development. UPDATE: Work continues on multiple sites in the village. Buildings on Via Toscana and Artisan Way opened in 2024 and are now experiencing near full occupancy. The site is operating as a new focal point in town and offers retail and restaurant offerings that draw from a large market area. Tuscan Village as a whole has contributed to Salem’s designation as a Housing Champion. New building introduced in 2024 include an 84,000 square foot building with mixed office/retail/restaurant spaces and a 235,000 square foot building with mixed retail/restaurant/residential (230 units) spaces plus several smaller, standalone single use retail buildings. Construction is underway on one additional 474,000 square foot building, with mixed retail/grocery/residential (300 units) spaces with associated underground parking and garage spaces. | H, IU, CV | On-going. | $1 billion | This project is anticipated to create and retain in roughly 5,000 permanent jobs in a wide variety of sectors, including retail, hospitality, food, health care, and professional sectors. | Private Developer
Salem/Tuscan Village Off-site Infrastructure | Salem | Crayton Brubaker (Community Development Program Manager) | 2026-03-27 | DESCRIPTION: This project covers a necessary off-site infrastructure improvement needed adjacent to, and in conjunction with, Tuscan Village. The Ring Road project will create three new roadway links with new intersections on Rt. 28. UPDATE: The Town received federal approvals for the crossing at Brunello Road in 2024-2025. No other significant progress on the ring roads development. | IU, T | On-going. | $10 million | 250 | EDA Grant, NH DOT grant, Municipal, Private Developer
Route 1 Expansion North | Seabrook | Bill Manzi (Town Manager) | 2026-02-18 | DESCRIPTION: The proposal is to widen Route 1 from New Zealand Road north to the Hampton Falls town line from three lanes to four. UPDATE: The project is included in the state's draft 2027-2036 Ten Year Plan, with financing modified to limit Seabrook’s financial responsibilities to the amount currently included in the exaction fund. | IU | Preliminary engineering: 2027; Construction: 2030 | $3.8 million (Total cost in TYP: $4.317 million) | 10 | NH DOT, State and Federal funding, Local Exaction Fees
Yankee Fishermen's Cooperative Infrastructure Improvements | Seabrook | Kim D'Orazio (Yankee) | 2026-02-27 | DESCRIPTION: Yankee Fishermen's Cooperative requires a number of upgrades and infrastructure improvements in order to meet regulatory compliance and ensure revenue meets or exceeds expenses. Phases 1 and 2 include required repairs and upgrades, Phase 3 focuses on a business needs study. UPDATE: Phase 1: To date, the following improvements have been completed: Garage Doors, Ice Machine Building Roof, Warehouse Ceiling Heat System. Remaining Phase 1 Item: Bait Cooler Repair/Replacement. Phase 2 includes: Fuel Dispenser Replacement (Fleet Boats), New Hoists, and New Insulated 174-Gallon Bins. Phase 3 includes: Replacement of Retail Display Cases and re-establishing in-house filleting and packaging capacity. | W | 2024-2027 | Phases Remaining in 1) $20,000 2) $86,676 3) UNK | This project will save approx.. 40 small businesses (fishing boats) and 4 employees. | Grants
Windham Greenway Recreation Trail | Windham | Alex Mello (Community Development Director) | 2026-03-11 | DESCRIPTION: Windham is looking to improve 2.5 +/- miles of the Greenway Recreational Trail located west of I-93; which is currently owned by the Town and runs over much of the abandoned Boston and Maine Railroad right-of-way. This trail is part of the Granite State Rail Trail. The existing project area is narrow and traverses over rough terrain unsuitable and unsafe for many pedestrians or bicyclists to use. The remoteness and limited visibility of the area also poses potential safety hazards to users. Opening this area of trail and paving a path for use improves safety by enhancing crossings that will limit the potential for accidents with vehicles, encouraging more users will deter crime, and an improved surface will reduce injury to users. This improvement will also provide an alternative to driving on key roads in town and will provide additional mobility options to the public. UPDATE: New Project. | T, E, CV | 5-10 years | $2.4 million | Temporary construction jobs. | Federal and State grants, Municipal
Windham Water Line Extension | Windham | Alex Mello (Director of Community Development) | 2026-03-11 | DESCRIPTION: A water needs and assessment study to help the town determine the costs associated with extending the public water system, followed by implementation of recommendations as funding becomes available. UPDATE: NE DES commissioned Pennichuck Water Works, Inc. to conduct Development Charge Study to assess the economic viability of implementing a System Development Charge (SDC) that could be collected from anticipated existing and future users to offset the capital investment of an extension of public water along Route 111 in Windham, NH. The overall conclusion was that full cost recovery through an SDC fee for either alternative would be improbable, and additional incentives or adjusted expectation of cost recovery should be explored. | IU | 5-10 years | $11.56 million | UNK | State, Municipal, Private Investment
COAST Facility Expansion | Seacoast Region/ COAST | Rad Nichols (COAST) cc: Scott Bogle (RPC) | 2026-01-20 | DESCRIPTION: The Cooperative Alliance for Seacoast Transportation (COAST) existing facility in Dover is inadequate to meet system and regional needs. The project proposes to expand its existing facilities to include administration space, operations/dispatching space, a regional call center, maintenance bays, and indoor bus storage. Although located outside the REDC CEDS region, COAST services the Seacoast area, including the communities of Portsmouth and Newington. UPDATE: The final design for the new facility is being finalized and nearly complete. Revised project cost estimates were completed inn 2025. COAST applied for a $3.5 million BUILD grant in February 2026. | T | design completed 2026; project bid 2026; construction 2027-2028 | $19.54 million | UNK | FTA grant, CDFA tax credits, private foundations/ fundraising
NH Seacoast Greenway | Seacoast Region/ RPC | Scott Bogle (RPC) | 2026-01-13 | DESCRIPTION: THE NH Seacoast Greenway is part of the U.S. East Coast Greenway, running from Portsmouth to Seabrook. UPDATE: Phase 1 was completed and opened in September 2024. Phase 1A (1.6 miles in Hampton from the North Hampton town line to Drakeside Road) began construction in fall 2025 and will be completed in spring 2026. The corridor communities of Portsmouth, Greenland, Rye, North Hampton and Hampton are working with RPC on trailhead facilities. Two trailheads with parking are in place in Portsmouth and North Hampton. Congressional earmark funding has been secured for two more sites in Portsmouth. Additional sites in Greenland and North Hampton are being planned. Phase 2 in Seabrook is programmed in the NHDOT Ten Year Plan ($1.8M) for construction in 2030. Engineering for Phase 3 through Hampton Falls and southern Hampton will begin in 2026 using a $1.45M USDOT RAISE grant secured by RPC. Construction funding ($5.8M) is programmed for 2032 in the current approved Ten Year Plan, though proposed for delay beyond 2036 in the draft 2027-2036 Ten Year Plan. Trail advocates, RPC, corridor communities and elected officials from the region are working with NHDOT to restore funding for the construction phase by 2032. The nonprofit NH Seacoast Greenway Alliance (NHSGA) is working with RPC and corridor communities to develop funding, recruit and trail volunteers for trail maintenance, and promote the trail once completed. The project remains a priority in MPO Long Range Transportation Plan. | T, E | Hampton-Portsmouth segment completed; Hampton 2026; Seabrook 2030 years; Hampton Marsh 2032. | Hampton-Portsmouth: $9.6 million; Seabrook-Hampton: $7.5 million | UNK | CMAQ, STBG, TAP, RTP, Private Sector
REDC EDA Revolving Loan Fund | Region & State/ REDC | Dan Gray, REDC | 2026-03-17 | DESCRIPTION: To obtain a Revolving Loan Fund (RLF) grant award with the EDA as a source of financing for REDC. UPDATE: An application was made and approved in 2024, however it has been held over for additional review since January 2025. | W, CV | Project ready to go as soon as grant is awarded. | $2 million | 250+ created and retained by companies receiving loans | REDC: $400,000; EDA/Federal: $1.6 million
Southern NH Workforce Corridor Pilot (Grades 1–8 Advanced Manufacturing & ReGen Valley Talent Pipeline) | Region/ Uncharted | Amber-Nicole Cannan (Executive Director, Uncharted) | 2026-02-18 | DESCRIPTION: The Southern NH Workforce Corridor Pilot is a phased 2026–2029 after-school workforce development initiative aligned to advanced manufacturing, regenerative medicine (ReGen Valley), logistics, and technology-enabled production sectors within the Merrimack–Londonderry–Derry–Nashua corridor. The program establishes a Grades 1–8 workforce development continuum designed to strengthen early STEM identity formation, applied engineering exposure, and middle school career pathway awareness aligned to corridor industry demand. Primary implementation communities within the REDC region include Nashua (SAU42), Auburn (SAU 15), independent schools in Londonderry, Londonderry (SAU 12), Derry (SAU 10), and Merrimack (SAU 26). Phase 1: Pilot after-school cohort deployment in Nashua, Auburn, and participating Londonderry schools. Phase 2: Expansion to Londonderry and Derry with formal employer engagement alignment. Phase 3: Expansion to Merrimack; corridor workforce evaluation and REDC scaling model development. UPDATE: New Project. | C, W, E | Phase 1: 2026-2027; Phase 2: 2027-2028; Phase 3: 2028-2029 | $250,000 – $400,000 total corridor investment (2026–2029 CEDS cycle); $8,000 per cohort unit; illustrative midpoint scenario approximately $350,000. | Two to eight part-time, possibility to expand to full-time. | Industry sponsorships, Grants, Private foundations, Corporate philanthropy, Municipal or district partnerships
PROJECTS REMOVED
Wason Pond Recreation Area Bridge Replacement | Chester | Andrew Hadik (Town Planner) | 2026-03-18 | DESCRIPTION: Replace a 60+ year old, flood-damaged access bridge to the Wason pond Conservation and Recreation Area (WPCRA). The replacement bridge shall meet current environmental and climate change resiliency requirements and shall meet the needs of the fire department for weight and access. The project has 3 phases: 1) engineering, permitting, bid package preparation, 2) bid review, 3) construction. UPDATE: The required funding has been obtained. NH DES has approved the wetlands permit. Construction commenced in March and was completed in early spring 2026. | IU, E, CV | Construction in 2026. | Phases 1/2: $64,000, Phase 3: $389,000 | 12 temporary construction jobs | 50% from NH Parks & Wildlife grant & 50% from Chester Conservation Commission fund
Epping Road Economic Development Initiative | Exeter | Darren Winham (Economic Development Director) | 2026-04-03 | DESCRIPTION: Extend sewer and waterlines and improve the roadway and signalization of Epping Road, from Continental Drive to and through the Rte. 101 interchange using a TIF. UPDATE: Construction activities were completed in 2025. The project is complete. | IU | Completed. Began 2015, ended 2025. | 6364000 | N/A | TIF District/ Town Funded
Bicentennial Wall Reconstruction | Hampton | Jen Hale (DPW Director) cc James Sullivan (Town Manager) | 2026-03-10 | DESCRIPTION: Reconstruction of the existing seawall located the northerly end of North Beach in Hampton (at Bicentennial Park). The project is designed and ready to bid. UPDATE: The Project was completed in 2025. | IU, E, CV | Completed | Final Cost: $2,659,780 | 0 | $2,552,188 - Town Appropriation - Bond $52,592 -FEMA $55,000 - NHDOT
Kings Hwy Flood Control Improvements | Hampton | Jen Hale (DPW Director) cc James Sullivan (Town Manager) | 2026-03-10 | DESCRIPTION: The project scope includes improving the drainage system on Greene Street, Gentian Street, Meadow Pond Road, and Kings Highway to reduce the ongoing flooding associated with chronic tidal flooding and sea level rise. The improvements include new catch basins and gravity drain lines, and the reconstruction of an old sewer pump station to redirect collected water from Meadow Pond. UPDATE: The project was completed in May 2026. | IU | Construction 2024-2026 | 4305390 | 0 | NH DES CFRING Grant, Municipal
Kingston Landfill Community Solar Farm | Kingston | Glenn Coppelman (Select Board) | 2026-01-13 | DESCRIPTION: The construction of a 5-6 megawatt solar farm on its capped landfill property on Route 125 near the intersection with Route 107 (Marshall Road). It has entered into a land Option Agreement with ReVision Energy that will allow ReVision to begin the due diligence and engineering portion of the project. The plan is to produce electricity for the grid - enough to offset the power used by more than 1,000 homes, reduce the Town's carbon footprint, and generate revenue from lease of the land for this purpose. ReVision Energy will develop the project. UPDATE: The project is not moving forward at this time. ReVision Energy, during its due-diligence phase, determined that the cost of interconnection to the grid is extremely high, thus prohibiting the project from moving ahead to design and implementation. | IU | N/A | N/A | N/A | N/A
Salem Master Plan Update | Salem | Crayton Brubaker (Community Development Program Manager) | 2026-03-12 | DESCRIPTION: The town has initiated an update to its Comprehensive Master Plan. The current plan was last was updated in 2017 by internal staff with little public involvement. In 2023, the town established a Master Plan Steering Committee with representatives from multiple boards and commissions throughout Town to guide the process. The town's planning director staffs the committee. In December 2023, the committee selected Utile Design out of Boston, MA to be the town's consultant. UPDATE: The Salem Master Plan was completed and adopted by the Planning Board in April 2025. Town staff is actively taking steps to implement aspects of the Master Plan. A comprehensive zoning update will begin in 2026. | CV | Completed | 150000 | Five | Municipal
Career Pathway Program | Seacoast - Manchester areas / Hampton Area Chamber of Commerce | John Nyhan (Hampton Area Chamber President) | 2026-03-25 | DESCRIPTION: To provide initial job training in plumbing, electrical, oil/heat, and HVAC to 260 high school students over seven school semesters. The program, sponsored by the Hampton Area Chamber, creates a cooperative relationship with high schools in the Seacoast and greater Manchester areas, partnering with NH School of Mechanical Trades and ApprenticeshipNH. UPDATE: The initial funding ran out and the program finished in the spring of 2025. | W | March 2022 - June 2025 | $342,550 + $2,000 for scholarships. | UNK | State GOFERR Program funds; NH BEA/ Seacoast CEDR