## 2025 Final List for ONLINE
2025 Priority Project List
Project Name | Location/ Sponsor | Project Description and Update | 2025 Priority Area/s | Timeline | Estimated Costs | Estimated Jobs | Funding Sources
Halls Village Road Reconstruction | Chester | DESCRIPTION: The project is intended to upgrade approximately 1.2 miles of a narrow and poor condition Class V town road. The project also includes the upgrade of two undersized culvert locations for stream crossings which have occasionally overtopped the road. HVR is a bypass that is heavily used as a connector by the residents of Chester and the surrounding towns of Derry, Sandown, and Fremont, and also commercial trucking and contracting traffic operating regionally in this area. UPDATE: The surveying, geotechnical borings, hydrological & hydrologic engineering for the culverts, and the under-drainage, new ditches and driveway culverts, and reconstruction and paving of the wearing course for the road have all been completed. The culverts still need to be replaced. It has not yet been decided when to pave the wearing course. | IU, E | Initial site work and engineering has been completed Construction in phases: July 2026 - November 2028 | construction cost: $1,770,000 | 34 temporary jobs; retaining 14 for businesses on HVR | Municipal
Wason Pond Recreation Area Bridge Replacement | Chester | DESCRIPTION: Replace a 60+ year old, flood-damaged access bridge to the Wason pond Conservation and Recreation Area (WPCRA). The replacement bridge shall meet current environmental and climate change resiliency requirements and shall meet the needs of the fire department for weight and access. The project has 3 phases: 1) engineering, permitting, bid package preparation, 2) bid review, 3) construction. UPDATE: The studies and design have been completed. The project was approved at the May 2024 Annual Town meeting to funding half of the cost. However, permitting delays and other issues beyond the Town's control have increased the originally estimated cost by $144,000. The town is now waiting to see if additional funding will be approved to cover the Town's share of this cost increase. | IU, E, CV | Construction in 2025 or 2026. | 464000 | UNK | 50% from NH LWCF grant & 50% from Chester Conservation Commission fund
Abbott Court | Derry | DESCRIPTION: This project will provide a public parking garage with retail and workforce/affordable housing components above. A potential second commercial building is being considered. (updated 2024) UPDATE: Permitting and design review underway. Anticipate groundbreaking in 2025. | H, T | Groundbreaking for garage in Summer 2025 | $40+ million | 25 new/ retained | Municipal Bond; Public/Private; Direct Sale; Grants
Derry Rail Trail Extension | Derry | DESCRIPTION: This project will extend the existing Derry Rail Trail to the Londonderry town line, tying into the regional trail system and Granite State Rail Trail system. The proposed extension is 1,900 feet. UPDATE: No changes. | T, E | 2026-2028 | 969800 | temporary construction jobs | Federal Transportation Alternative Funds, Municipal
Derry Route 28 Sewer Interception Extension | Derry | DESCRIPTION: Extend the sewer line from Route 28 at Berry Rd south to Ryan's Hill as identified in the town's Master Plan. The extension includes 105+/- acres of commercially-zoned properties, much of which remains vacant. As Derry has very limited commercial land available for development, public sewer would maximize the economic development of this area. 3,600' of gravity sewer line and 1,925' of pressure line is proposed. UPDATE: Due to the high volume of planned road projects in 2025, the town has delayed the project until 2026. | IU | 2026 | $4.2 million | UNK | Municipal bond, Water Wheeling revenues
Epping Road Economic Development Initiative | Exeter | DESCRIPTION: Extend sewer and waterlines and improve the roadway and signalization of Epping Road, from Continental Drive to and through the Rte. 101 interchange using a TIF. UPDATE: Construction was initiated in June 2024 with shoulder widening, utility relocation, and drainage work completed by November 2024. Additional funding was approved via an amendment to the TIF financing plan in March 2025. Construction activities will resume in May 2025 with full completion expected by the end of 2025. | IU | On-going with completion in 2025. | $4 - $7 million for outstanding project components. | UNK | TIF District
New Police Station and Fire Substation | Exeter | DESCRIPTION: Construct an approximately 23,000 square foot new police station and fire substation. The existing police department will be relocated to the new facility and a portion of the downtown fire station will be relocated to the new substation. UPDATE: Project underway, construction management has been selected. | IU, CV | 2024-2026 | 17300000 | temporary construction jobs | Municipal bond
Squamscott River Sewer Siphons & Webster Avenue Pump Station | Exeter | DESCRIPTION: This is a two phase project to increase sewer capacity which will allow for future growth and prevent the likeliness of sanitary sewer overflows. The first phase includes replacing three parallel inverted sewer siphon pipes under the Squamscott River. The second phase includes upgrading the current flow capacity at the Webster Avenue sewage pump station. UPDATE: The Sewer Siphons project reached substantial completion in July 2024 and the siphons are now operational. A construction contract was awarded for the Webster Ave Pump Station project in April 2024 and construction activities began July 2024. Construction has been ongoing and will continue through the end of 2025 with substantial completion expected by March 2026. | IU | Construction is underway, completion estimated in 2026 | Phase 1 - Squamscott River Siphons $3.36 million for the first; next two costs UNK Phase 2 - Webster Ave Pump Station $6.5 million | N/A | CDS (federal), NH ARPA, NH DES CWSRF Grants, Municipal
Bicentennial Wall Reconstruction | Hampton | DESCRIPTION: Reconstruction of the existing seawall located the northerly end of North Beach in Hampton (at Bicentennial Park). The project is designed and ready to bid. UPDATE: Construction began in January 2025 with an anticipated completion by June 30, 2025. | IU, E, CV | Short term. | $3 million | UNK | Municipal Warrant Article
Hampton Wastewater Treatment Plant | Hampton | DESCRIPTION: Implementation of a three-phase design and construction project necessary to ensure continued reliable and efficient operation of the town's existing wastewater treatment plant and to comply with the town's effluent discharge permit. UPDATE: Phase I is complete. Phase II is funded and under final design, with bidding in June 2025 and construction anticipated for late summer 2025. | IU | Phase 1: Completed Phase 2: 2024-2026 Phase 3: UNK | Phase 2: $15,700,000 | UNK: but will retain jobs and allow for future development | Municipal, CWSRF, ARPA, SAG/SAG Plus
Kings Hwy Flood Control Improvements | Hampton | DESCRIPTION: The project scope includes improving the drainage system on Greene Street, Gentian Street, Meadow Pond Road, and Kings Highway to reduce the ongoing flooding associated with chronic tidal flooding and sea level rise. The improvements include new catch basins and gravity drain lines, and the reconstruction of an old sewer pump station to redirect collected water from Meadow Pond. UPDATE: The project was put to bid in the fall 2024, with bids exceeding the original cost estimates and funding. The town and numerous stakeholders worked with NHDES and the NH Governor and Council to secure the additional funding. Additionally, the project was modified to meet the new funding constraints. The project is under construction, with an anticipated completion in late summer 2025. | IU | Construction 2024-2025 | $4.1 million | N/A | CFRING Grant/ARPA, Municipal
Winnacunnet Road Reconstruction | Hampton | DESCRIPTION: Reconstruction of Winnacunnet Road from Lafayette Road to Ocean Boulevard. Includes replacement of failing utility infrastructure and sidewalks, as well as surfacing of the roadways. UPDATE: Due to other townwide needs, the project schedule has been adjusted and temporary repairs completed. Funding is not secured. | IU | 2028+ | 12705000 | N/A | TAP, CWSRF, Municipal
Hampton Route 1A Improvements | Hampton/ Hampton Beach Area Commission | DESCRIPTION: Design, engineering, and complete reconstruction of the roadway, infrastructure, and sidewalks for critical sections of Ocean Blvd (Route 1A) from the new Seabrook-Hampton Bridge (currently known as the Neil R Underwood Bridge) to the High Street intersection. Work shall be in concert with the design and construction of the new Seabrook-Hampton Bridge. UPDATE: In the past 12 months, NHDOT has been holding public neighbors meetings. The project continues to be in the design phase with final design to be reviewed in July, 2025. The south end of 1A will be redesigned to coordinate with the new Seabrook-Hampton Bridge. | IU, T | Construction anticipated to begin in 2024 | Phase 1: engineering & partial construction $9.9 million Phase 2: construction $52-70 million | UNK | UNK
Hampton U.S. 1/NH 101 Interchange Realignment | Hampton/ RPC | DESCRIPTION: Realignment of the U.S. Route 1 and NH Route 101 interchange in Hampton. UPDATE: The project is listed in the NHDOT 2025-2034 Ten Year Transportation Plan (TYP), approved June 2024. Project construction is scheduled for FY2029. The project remains a priority in the RPC MPO Long Range Transportation Plan. | IU, T | 2029+ | $8.1 million (2029 dollars) | UNK | National Highway System (NHS); Surface Transportation Block Grant (STBG)
Kingston Landfill Community Solar Farm | Kingston | DESCRIPTION: The construction of a 5-6 megawatt solar farm on its capped landfill property on Route 125 near the intersection with Route 107 (Marshall Road). It has entered into a land Option Agreement with ReVision Energy that will allow ReVision to begin the due diligence and engineering portion of the project. The plan is to produce electricity for the grid - enough to offset the power used by more than 1,000 homes, reduce the Town's carbon footprint, and generate revenue from lease of the land for this purpose. ReVision Energy will develop the project. UPDATE: ReVision Energy continues with the preliminary engineering design and cost details and coordinating with Unitil for the "interconnection" logistics. | IU | 2024-2026 | $15-$20 million | temporary construction jobs | Private investors
The Village on Technology Hill PUD | Londonderry | DESCRIPTION: The Village on Technology Hill PUD is a mixed-use development encompassing approximately 110 acres. The project is organized into 3 primary zones: Industrial - this area includes approximately 330,000 square feet of industrial and office space Residential - this area includes a residential development of 439 market rate units distributed across 9 buildings offering one-, two-, and three-bedroom units. The buildings encircle a village green featuring amenities such as a playground and dog park. Commercial - this area includes a general retail store and childcare facility serving residents and employees of nearby businesses. UPDATE: New Project | H, C, W, CV | Project started in 2024 and is ongoing | Total construction cost estimated at $160 million | 300+ jobs | Private developer
Woodmont Commons Project | Londonderry | DESCRIPTION: Development of a 600-acre mixed-use, approved Planned Unit Development (PUD) Master Plan. Permitted for up to 1.8 million square feet of commercial space, over 1,400 residential dwelling units, plus hotel, institutional, and civic uses. UPDATE: Construction on Phase 1 continues. Significant changes in the last 12 months include: a 246-unit multifamily residential development consisting of eleven buildings has started construction and a second medical office building of 30,000 square feet has been approved. A 250-unit single family cottage court style residential development is in design and a 750,000 square foot industrial commerce area is in design review. | H, IU, W | On-going | UNK | Phase 1: 600 new jobs; Remaining Phases: over 3,000 new jobs | Private Developer
Imagine Main Street | Nashua | DESCRIPTION: Designing Main Street to function as a destination instead of a thruway. The city is committed to building on the momentum from the significant recent and ongoing investments in our downtown and realize the community-led vision for Main Street outlined in the recently adopted Master Plan, Imagine Nashua. Continued investment in our downtown, comprised almost entirely of neighborhoods identified by the DOT as Areas of Persistent Poverty and Historically Disadvantaged Communities, will increase economic opportunities and improve quality of life for our residents. The Imagine Main Street project will directly confront the inequities the current vehicle-oriented design of the corridor creates for those without personal vehicles, as well as incorporating green infrastructure to help mitigate the disproportionately negative environmental impacts on residents of the proposed project area. Nashua's downtown is an important economic driver of the city, and the city strives to make it a welcoming, walkable, and enticing destination for residents and visitors alike. UPDATE: The city applied for funding though the RAISE grant program, but it did not receive the award. | T, CV | Planning 2025; Construction 2026-2028 | Design/Planning: $3.5 million Construction: $30+ million | UNK | Municipal bond
Nimco Redevelopment | Nashua | DESCRIPTION: The redevelopment of a city-owned parcel of land known as the "Nimco Property," a defunct building with adjacent land area on a brownfield site. The property is approximately 3+ acres in land area. It is located in downtown Nashua off the Veterans Memorial Parkway and the Nashua River. It will need environmental cleanup, demolition of the existing mill building, and redevelopment of housing. UPDATE: The Master Development Agreement between the city and developer is being finalized. Due to a fire at the site, the city moved up the development timeline, and demolition is scheduled for late spring 2025. | H, E | Negotiations with private developer in 2024. Demolition scheduled for June 2025. | Demolition: $1.5 million; Land: $5 million; Remediation: UNK; Construction: $15+ million | none | Private Developer
Nashua Public Library | Nashua | DESCRIPTION: The Nashua Public Library Building is in need of a full renovation to bring the building up to code. This includes major improvements to the accessibility of the bathrooms, stairs, sprinklers, lighting, etc., as well as a complete overhaul of the building envelope inside and out. This will also include a programmatic study of what the modern library needs. It is currently being used for a library and a de facto community center and will need to make major improvements to the physical space in order to accommodate the modern uses of the library. UPDATE: Space needs assessment is underway and to be completed May 2025. RFP for development opportunities with the library, parking, and public space included to be released after space needs study is completed. | CV | Underway. | $30+ million | 75 | Municipal bond, P3
Mohawk Tannery Cleanup & Development | Nashua | DESCRIPTION: The old Mohawk Tannery is being redeveloped into 540 housing units including some affordable units. The site is Brownfield, and the first step in this process is environmental cleanup from the tanning activities that have left toxic chemicals in most of the property. The next step is apartments, with 20% affordable, and then condos. There will be six buildings and a very large public open space and a pedestrian bridge over to Mine Falls Park. UPDATE: The Nashua Planning Department is reviewing the site plans. | H, E | Site clean up is scheduled to begin in 2026. | Cleanup: $23 mil; Site development: $300+ million | UNK | Federal, State, Local, Private
Redevelopment of Elm Street School | Nashua | DESCRIPTION: The Elm Street Middle School closed in June 2024 and reverted to city ownership. After community outreach and input, the city is focusing on midrise housing for the site, possibly reusing the building and maintaining the Keefe Auditorium as a public theater. The project has gone out for RFP to see what private development can bring to the project. We hope to see at least 300 housing units over the entire acreage and a reinvestment in the Keefe Auditorium. UPDATE: New Project | H, CV | Select developer in 2025, start construction in 2026 with 3-5 years of phased development. | Housing Project $300+ million Auditorium: $30+ million | UNK | Private funding, Municipal funding, LIHTC, Nashua's Housing Trust, NH Invests
McIntyre Road Bridge Study and Intersection Design | Newington | DESCRIPTION: Town owned McIntyre Bridge, was built in 1972 as a public roadway crossing Pease Air Force Base. The bridge overpass crosses over a former Air Force roadway, separated vertically for base security reasons. The former Air Force road and surrounding land are now open to the public as part of a Great Bay National Wildlife Refuge and the Pease Development Authority, and the vertical separation of these roads now hinders public access. A 2024 NHDOT bridge inspection rated the bridge deck width “intolerable” listed for high priority replacement. This project will perform a feasibility study of alternatives including the possible bridge and fill removal to provide an at-grade intersection and enhanced public access, reducing resident travel distance by 2.5 miles. UPDATE: New Project | IU, E | Immediate once funding is secured | 288750 | none | Federal/State Sources $258,750 Local Sources $30,000
Newington Port Roadway Improvements | Newington/ Newington and Portsmouth | DESCRIPTION: The project involves the full depth reconstruction of approximately 2,700 LF or 74,800 sf of roadway along the eastern portion of Gosling Road, and 11,330 LF or 401,100 sf of Shattuck Way in order to improve the base material of each roadway resulting in improve load capacity. In addition, certain portions of Shattuck Way will be raised and the corresponding drainage improved to correct the flooding conditions that have been experienced. The proposed improvements will enhance the roadways’ sustainability and reliability as the primary access route to other inland transportation corridors. UPDATE: In 2024, the town completed the reclamation of a portion of Shattuck Way, to a 10” depth from construction joint near River Road to joint near Newington Energy parking lot, approximately 2,600 LF. There remains approximately 2,700 LF of Gosling Road and 8,730 LF of Shattuck Way that requires design and construction. Design work on this portion can start as soon as additional funding is secured. | IU | Design work can start as soon as funding is secured. | 2629000 | UNK | Federal and State trans-portation grants, municipal funding
U.S. Route 1 Sidepath Construction | Portsmouth | DESCRIPTION: Creation of a walkable and bike-able connection for neighborhoods and destinations along Route 1 through construction of ten ft. sidepaths on each side of road in available NH DOT right-of-way. This will be a phased project: the first phase is the design work from the intersection of Elwyn Road/Peverly Hill Road to Heritage Ave. to correspond with the NH DOT Route 1 Corridor. Additional sections will be designed as part of Phase 2, and construction of the project is Phase 3. Because of the corridor project and DOT involvement, final costs may be more that the city portion. UPDATE: NH DOT and the city held public advisory meetings in 2024 & 2025, a public meeting July 2024, and a work session with City Council November 2024. NH DOT aims for a public hearing in 2025. Delays continue to push the project out. | CV | Planning and Design: 2025-2027; Construction: 2028-2030 | $19.2 to $24.9 million | UNK/Indirect | Capital Improvement Plan, Municipal, State
Salem Bike-Pedestrian Corridor | Salem | DESCRIPTION: The completion of a 5.1 mile rail trail on the former Manchester & Lawrence rail line. The Salem section is the most southern segment of the Granite State Rail Trail, which will run from Salem to Lebanon, NH. Currently the northern (approx.) two miles is paved and complete. Plans and funding are in place for the section from Main St. to Cluff Crossing Rd. Approx. two miles of trail south of Cluff Road remain. There are additional projects that will need to be developed to help support corridor. UPDATE: Phases IV and V (Main Street to Rockingham Park Blvd) will begin design soon. Phase VI (Rockingham Park Blvd to Cluff Crossing Road) will beginning construction in 2025. Design work on additional phases will start as grant opportunities arise. | T, E | Phases I-III are complete; Phases IV-V design soon; Phase VI construction in 2025; Phase VII+ are UNK SHORT TERM | Completed phases $2+ million; Phases IV-VI: $1.9 million; Phases VII+: UNK; Hampshire Road area improvements: $240,000; Brunello Road Bridge: $1.5 million | UNK | CMAQ, TTAP, EDA, Impact Fees, Private Developer
Salem Master Plan Update | Salem | DESCRIPTION: The town has initiated an update to its Comprehensive Master Plan. The current plan was last was updated in 2017 by internal staff with little public involvement. In 2023, the town established a Master Plan Steering Committee with representatives from multiple boards and commissions throughout Town to guide the process. The town's planning director staffs the committee. In December 2023, the committee selected Utile Design out of Boston, MA to be the town's consultant. UPDATE: The Master Plan Steering Committee worked throughout 2024 and 2025 to engage public input and develop and guide the Master Plan. The Master Plan focuses on four key areas: Gathering Spaces (including Depot Village and Historic Town Center), Town Connectors (Rail Trail and sidewalk infrastructure), a Mixed Use Core, and Missing Middle Edges (variety of housing development). It is anticipated that the Planning Board and Town Council will adopt the Master Plan by June 2025. | CV | 2024-2025 | 150000 | Five | Municipal
Salem Police Station | Salem | DESCRIPTION: The proposed project includes design, demolition of the existing building, construction of the new facilities, and temporary relocation of the Police Department operations during construction. The new Police Station building will be situated on the same site as the existing facility. The new police station will encompass an operational area on two levels of approximately 31,600 square feet (SF), 4,000 SF Training Range, and a 4,000 SF K9 Outbuilding. UPDATE: Demolition of the existing building began in April 2025. The Police Department has completed renovations to the DPW building where they will be temporarily relocated during construction. Construction will begin in spring 2025 and is expected to last until Fall 2026. | IU, CV | 2024-2026 | $38.6 million | retain 250 jobs | Impact fees, municipal bonds
Tuscan Village | Salem/ Tuscan Village Development | DESCRIPTION: Redevelopment of the former Rockingham Park Racetrack. The mixed-use project will include multifamily housing, retail, medical offices, office space, a hotel, restaurants, and a car dealership. The total project is 170 acres and will contain close to 2.5 million sq. ft. of development. UPDATE: Work continues on multiple sites in the village. Buildings on Via Toscana and Artisan Way opened in 2024 and are now experiencing near full occupancy. The site is operating as a new focal point in town and offers retail and restaurant offerings that draw from a large market area. Tuscan Village as a whole has contributed to Salem’s designation as a Housing Champion. New building introduced in 2024 include an 84,000 square foot building with mixed office/retail/restaurant spaces and a 235,000 square foot building with mixed retail/restaurant/residential (230 units) spaces plus several smaller, standalone single use retail buildings. Construction is underway on one additional 474,000 square foot building, with mixed retail/grocery/residential (300 units) spaces with associated underground parking and garage spaces. | H, IU, CV | On-going. | $1 billion | This project is anticipated to create and retain in roughly 5,000 permanent jobs in a wide variety of sectors, including retail, hospitality, food, health care, and professional sectors. | Private Developer
Salem/Tuscan Village Off-site Infrastructure (Depot Village) | Salem | DESCRIPTION: This project covers a necessary off-site infrastructure improvement needed adjacent to, and in conjunction with, Tuscan Village. The Ring Road project will create three new roadway links with new intersections on Rt. 28. UPDATE: In 2024, the Town began a Depot Master Plan process, which will be completed in 2025. Design and implementation of the Depot Master Plan will occur in future years in order to bring the various Town-owned parcels into a well programmed community space and recreational development. Additionally, design work on the remaining Ring Roads will continue in future years. | IU, T | On-going. | $10 million | 250 | EDA Grant, NH DOT grant, Municipal, Private Developer
Route 1 Expansion North | Seabrook | DESCRIPTION: The proposal is to widen Route 1 from New Zealand Road north to the Hampton Falls town line from three lanes to four. UPDATE: The town is working with the state and private developer on financing the project. | IU | 2-5 years | $6.5 million | UNK | NH DOT, Municipal, Exaction Fees, Private Developer
Yankee Fishermen's Cooperative Infrastructure Improvements | Seabrook | DESCRIPTION: Yankee Fishermen's Cooperative requires a number of upgrades and infrastructure improvements in order to meet regulatory compliance and ensure revenue meets or exceeds expenses. Phases 1 and 2 include required repairs and upgrades, Phase 3 focuses on a business needs study. UPDATE: The Coop received funding for the following items, garage door replacement (to meet food safety compliance), ice machine building roof, convection steamers (processing equipment), and new hoists. The remaining items outlined in Phase 1 and Phase 2—including bait cooler replacement, ceiling heat system, fuel dispenser, and insulated bins—are still unfunded and will require financial support to proceed. Additionally, the Coop would like to add a forklift to one of the phases. | W | 2024-2026+ | Phases 1) $70,000 2) $92,000 3) $30,000 + | This project will save apprx. 40 small businesses (fishing boats) and 18 employees. | Grants, Loans, UNK
Windham Water Line Extension | Windham | DESCRIPTION: A water needs and assessment study to help the town determine the costs associated with extending the public water system, followed by implementation of recommendations as funding becomes available. UPDATE: In 2022, the water line under Rt. 28 and a portion of Rt. 111 became active. To date, 81 connections have been made in Windham and more are expected this year. Extending it further down Rt. 111 to the west, will help more properties overcome water quantity and quality issues. This Rt. 111 extension will help mostly commercial properties and town-owned buildings. However, extending it down Range Road and other spurs off of Rt. 111 will help residential properties that also experience water quantity and quality issues. | IU | 5-10 years | $11+ million | UNK | Grants, Municipal, Private Investment
Career Pathway Program | Seacoast - Manchester areas / Hampton Area Chamber of Commerce | DESCRIPTION: To provide initial job training in plumbing, electrical, oil/heat, and HVAC to 260 high school students over seven school semesters. The program, sponsored by the Hampton Area Chamber, creates a cooperative relationship with high schools in the Seacoast and greater Manchester areas, partnering with NH School of Mechanical Trades and ApprenticeshipNH. UPDATE: Current funding for the program runs out in June of 2025. The Chamber continues to apply for additional funds both at the State and Federal level. Also, they are working with participating high schools for to provide interim funding. To date, 25 students have been hired after completing the program, with an additional 25 continuing with advance training. Approximately 240 students have completed the program. | W | March 2022 - June 2025 | $342,550 + $2,000 for scholarships. | UNK | State GOFERR Program funds; NH BEA/ Seacoast CEDR
COAST Facility Expansion | Seacoast Region/ COAST | DESCRIPTION: The Cooperative Alliance for Seacoast Transportation (COAST) existing facility in Dover is inadequate to meet system and regional needs. The project proposes to expand its existing facilities to include administration space, operations/dispatching space, a regional call center, maintenance bays, and indoor bus storage. Although located outside the REDC CEDS region, COAST services the Seacoast area, including the communities of Portsmouth and Newington. UPDATE: The project is under final design, which should be completed in Summer 2025. Plans to put the project out for bid in the fall. | T | design completed summer 2025; construction 2026-2027 | $17.3 million | UNK | FTA Section 5339 grant program, CDFA tax credits, Capital campaign
NH Seacoast Greenway | Seacoast Region/ RPC | DESCRIPTION: THE NH Seacoast Greenway is part of the U.S. East Coast Greenway, running from Portsmouth to Seabrook. UPDATE: Phase 1 (8.0 miles from Barberry Lane in Portsmouth to the North Hampton/Hampton town line) was completed and opened in September 2024. Phase 1A (1.6 miles in Hampton from the North Hampton town line to Drakeside Road) is anticipated to be completed in late 2025. The corridor communities of Portsmouth, Greenland, Rye, North Hampton, and Hampton are working with RPC on trailhead facilities. Two trailheads with parking are in place in Portsmouth and North Hampton. Congressional earmark funding has been secured for two more sites in Portsmouth. Additional sites in Greenland and North Hampton are being planned. Phase 2 in Seabrook is programmed in the NHDOT Ten Year Plan ($1.44M) for construction in 2030. Phase 3 through Hampton Falls and southern Hampton is currently in the Ten Year Plan ($5.85M) for construction in 2032. RPC secured a $1.45M USDOT RAISE grant to accelerate engineering and permitting for Phase 3 in 2025-2027, which should allow construction to move up to 2028-2029. The nonprofit NH Seacoast Greenway Alliance (NHSGA) is working with RPC and corridor communities to develop funding, recruit and trail volunteers for trail maintenance, and promote the trail once completed. The project remains a priority in MPO Long Range Transportation Plan. | T, E | Hampton-Portsmouth segment 2024; Hampton 2025; Seabrook 2030 years; Hampton Marsh 2032. | Hampton-Portsmouth: $9.6 million; Seabrook-Hampton: $7.5 million | UNK | CMAQ, STBG, TAP, RTP, Private Sector
PROJECTS REMOVED
High Street Reconstruction | Hampton | DESCRIPTION: Reconstruction of High Street from Lafayette Road to Mill Pond Lane. Includes replacement of failing utility infrastructure and sidewalks, as well as surfacing of the roadways. UPDATE: This project was completed in August 2024. Total project cost was $6.9 million. | N/A | Completed in 2024. | Final costs: Investigation and Design: $449,825: Construction: $6,437,520 | N/A | Municipal